# U.S. Real Estate JV Setup Project Plan

Date: 2026-06-03

Purpose: Turn the structuring memo into a practical startup roadmap for a four-partner Midwest real estate flipping venture with two U.S. citizens, one U.K. investor, and one Belgian investor.

Important limitation: This is a business implementation guide, not a legal opinion or tax opinion. The structure should be reviewed by U.S. tax counsel, a corporate attorney, a CPA experienced with foreign-owned U.S. corporations, and U.K./Belgian advisors before money moves.

# Updated Partner Facts

| Fact | Updated Answer |
| --- | --- |
| Risk appetite | No high-risk strategies or workarounds |
| Foreign investor tax residence | Both the U.K. national and Belgian national are UAE tax residents |
| Treaty posture | Do not assume U.K. or Belgium treaty benefits; no U.S.-UAE income tax treaty baseline |
| Foreign investor activity | Passive capital only; no U.S.-based services |
| First operating state | Wisconsin |
| Phase 1, Step 2 | Broken out into a separate decision tree: foreign-investor-decision-tree.md/html/docx |

These facts change the planning priority. The conservative base case should not rely on aggressive portfolio-interest planning or treaty-country workarounds. The planning focus should move toward clean ownership, estate-tax protection, bankability, Wisconsin compliance, and proper withholding.

# Executive Summary

The most practical baseline is:

- Form one U.S. C corporation as the tax blocker and operating parent.

- Use separate disregarded LLCs under that corporation for property title, liability separation, and state operations where useful.

- Do not let the foreign partners directly own the U.S. corporation until estate tax planning is reviewed.

- Treat foreign money as either equity or properly documented debt. Do not assume shareholder debt qualifies for the portfolio interest exemption if a foreign lender owns 10% or more of the corporation's voting power.

- Open U.S. banking only after the entity structure, EIN, ownership chart, capital plan, and source-of-funds package are ready.

- Build withholding, Form 5472, Form 1042/1042-S, and state compliance into the operating calendar from day one.

Plain-English bottom line: the U.S. blocker helps keep the foreign partners from being directly in the U.S. real estate business, but it does not make the venture tax-free. The best financial setup is the one that balances tax efficiency with defensibility. The highest-risk shortcuts are weak shareholder loans, undocumented related-party interest, direct foreign ownership of U.S. shares without estate planning, and casual money movement through personal accounts.

# Working Recommendation

| Area | Recommended Starting Point | Risk Level |
| --- | --- | --- |
| Operating entity | U.S. C corporation taxed as a corporation | Medium |
| Property ownership | State LLCs disregarded to the U.S. C corporation, especially where multiple properties or states are involved | Medium |
| Foreign investor ownership | Review foreign holding companies before direct ownership of U.S. shares | High |
| Capitalization | Mix of common/preferred equity and carefully documented debt only after tax review | High |
| Portfolio interest | Do not rely on it if foreign lenders hold 10% or more voting power | High |
| Banking | One main operating bank account plus segregated project/escrow tracking | Medium |
| Compliance | CPA-managed federal, state, withholding, and related-party reporting calendar | High |
| Professional review | Required before formation documents are signed and before foreign capital is wired | High |

# Phase 1 - Decisions Before Formation

Do this before filing any entity paperwork. These decisions affect taxes, banking, partner rights, and exit planning.

| Step | What To Do | Why It Matters | Professional Review |
| --- | --- | --- | --- |
| 1. Confirm tax residence | Confirm whether the U.K. and Belgian partners are tax residents of the U.K., Belgium, UAE, or somewhere else. | Treaty benefits depend on tax residence and beneficial ownership, not nationality or where the money sits. | U.S. international tax counsel plus U.K./Belgian advisors |
| 2. Confirm investor type | Decide whether each foreign partner invests personally, through a foreign company, through a trust, or through a new holding company. | This drives estate tax, treaty rates, bank KYC, withholding forms, and reporting. | U.S. tax counsel and foreign counsel |
| 3. Decide ownership economics | Write down voting rights, profit split, losses, preferred return, capital calls, and exit rights. | Tax treatment follows the legal and economic deal. A vague deal creates tax and partner disputes. | Corporate attorney and CPA |
| 4. Choose first states | Pick the first Midwest states for acquisitions. | State registrations, tax returns, title rules, and local counsel needs are state-specific. | Real estate attorney and CPA |
| 5. Decide who manages | Identify who signs contracts, deals with brokers, approves purchases, and controls bank wires. | Banks, title companies, and auditors will ask who has authority. | Corporate attorney |
| 6. Decide whether foreign partners perform U.S. work | Foreign partners should avoid U.S.-based services unless planned. | U.S. services may create personal filing, visa, payroll, and withholding issues. | Immigration and tax counsel |

Deliverable: a one-page structure decision sheet signed off by the partners and advisors.

# Phase 2 - Professional Team

This structure should not be set up by a generic incorporator alone. The professional team should be small but specialized.

| Professional | What They Should Review | Why Needed |
| --- | --- | --- |
| U.S. international tax attorney | Blocker structure, foreign ownership, treaty eligibility, withholding, estate tax, debt/equity, FIRPTA, exit planning | This is the core risk area |
| U.S. CPA | Form 1120, Form 5472, 1042/1042-S, state returns, bookkeeping design, 163(j), property accounting | Keeps the structure compliant after setup |
| Corporate attorney | C corporation charter, bylaws, shareholder agreement, note documents, board consents, transfer restrictions | Makes the business deal enforceable |
| Real estate attorney/title counsel | Purchase contracts, title LLCs, closing certificates, state transfer rules, title insurance | Prevents closing-level tax and title mistakes |
| U.K. tax advisor | U.K. investor's home-country tax, foreign tax credits, treaty residence, reporting | U.S. planning may create U.K. consequences |
| Belgian tax advisor | Belgian investor's home-country tax, foreign tax credits, treaty residence, reporting | U.S. planning may create Belgian consequences |
| Banking relationship manager | Bank KYC package, foreign investor requirements, source-of-funds documentation, wire process | Avoids delays and account freezes |

Professional review points that should not be skipped:

- Whether foreign partners should own the U.S. corporation directly or through foreign holding companies.

- Whether any shareholder debt can be used safely.

- Whether the U.K. and Belgian treaty positions are actually available.

- Whether dividend, interest, or redemption payments are the best repatriation route.

- Whether the company could become a U.S. real property holding corporation for stock-sale exit purposes.

- Whether state-level taxes make one state of formation or operation better than another.

# Phase 3 - Entity Structure

## Recommended Basic Chart

| Layer | Entity | Owner | Purpose |
| --- | --- | --- | --- |
| Foreign investor layer | To be determined for each foreign investor | U.K. and Belgian investors | Estate tax and treaty planning |
| U.S. blocker | U.S. C corporation | Partners or holding companies | Main taxpayer and operating parent |
| Property title layer | State LLCs disregarded to U.S. C corporation | U.S. C corporation | Liability segregation and state title holding |
| Project bank accounts | Accounts owned by U.S. C corporation or title LLCs | U.S. C corporation control | Cash control and audit trail |

## Key Formation Choices

| Decision | Plain-English Explanation | Recommended Approach |
| --- | --- | --- |
| Corporation vs LLC taxed as corporation | A corporation is cleaner for foreign-owner blocking. An LLC can elect corporate tax treatment but may confuse banks and title companies. | Use a corporation unless counsel has a specific reason for an LLC election. |
| State of formation | Delaware is common for corporate law, but the company must register where it actually operates. | Use Delaware or a first operating state only after counsel weighs cost and state tax. |
| S corporation | S corporations cannot have nonresident alien shareholders. | Do not use an S corporation. |
| Title LLCs | LLCs can own individual properties while being ignored for federal tax if the C corp is the sole member. | Use when liability separation or state operations justify it. |
| Foreign holding companies | May reduce U.S. estate tax exposure for foreign partners. | Review before direct foreign ownership of U.S. shares. |

## Formation Steps

- Choose the final structure after professional review.

- Form the U.S. C corporation.

- Draft bylaws, initial board consent, stock ledger, shareholder agreement, and transfer restrictions.

- Issue shares only after the estate tax ownership question is resolved.

- Apply for EIN using Form SS-4 or the IRS online EIN process.

- If title LLCs are needed, form them as wholly owned subsidiaries of the C corporation.

- If any LLC must elect corporate or disregarded treatment, confirm whether Form 8832 is needed.

- Register to do business in each state where the company has offices, employees, repeated property activity, or state-law nexus.

- Create a compliance calendar for federal, state, city, county, annual report, registered agent, and franchise tax deadlines.

# Phase 4 - Capitalization Plan

This is the most important financial design step.

## Simple Capital Options

| Method | What It Means | Pros | Risks |
| --- | --- | --- | --- |
| Common equity | Partner buys stock and shares upside/downside | Simple legally | Dividends are not deductible; foreign direct ownership may create estate tax risk |
| Preferred equity | Partner gets priority return before common owners | Can match investor economics | Still equity, not deductible interest |
| Shareholder loan | Partner lends money to company under a note | Interest may be deductible and principal can be repaid | High risk if not real debt or if withholding is mishandled |
| Third-party debt | Bank/private lender lends to company | Cleaner debt treatment | User stated no institutional bank debt, and terms may be less flexible |
| Hybrid structure | Mix of equity and debt | Can balance tax and economics | Requires careful legal and tax drafting |

## Recommended Capital Workflow

- Build a 12-month acquisition budget.

- Decide minimum cash reserves for taxes, repairs, insurance, title, legal, and failed deals.

- Decide how much capital is permanent equity versus temporary deal funding.

- Model each partner's expected contribution.

- Model dividends, interest, and principal repayments separately.

- Review whether any related-party debt is respected as real debt.

- Set interest rates using market support, not partner preference.

- Draft formal promissory notes before money moves.

- Track each wire as either equity, loan principal, interest, expense reimbursement, or other.

- Never move partner money through another partner's personal account unless counsel specifically approves.

## Debt Rules In Plain English

For a loan to be respected, it should look like a loan a real lender would make. That means:

- Signed note.

- Fixed principal amount.

- Fixed or commercially supportable interest rate.

- Maturity date.

- Payment schedule.

- Default rights.

- Board approval.

- Accounting records separating principal and interest.

- No interest tied to property profits, appreciation, or flip margins unless tax counsel approves.

- Actual payments when due, or properly documented amendments.

## Portfolio Interest Warning

Do not assume the portfolio interest exemption solves withholding. If a foreign lender owns 10% or more of the voting power of the U.S. corporation, interest paid to that lender generally does not qualify as portfolio interest. With four 25% partners, this is a major problem unless the voting and debt structure is redesigned and reviewed.

# Phase 5 - Banking Setup

Banking should be treated as a compliance project, not just opening an account.

## Bank Account Structure

| Account | Owner | Use |
| --- | --- | --- |
| Main operating account | U.S. C corporation | General business cash, repairs, overhead, taxes |
| Acquisition account | U.S. C corporation | Funds reserved for property purchases |
| Tax reserve account | U.S. C corporation | Federal/state income tax and withholding reserves |
| Project subledger or account | U.S. C corporation or title LLC | Optional tracking by property |
| Escrow/title accounts | Title company | Closing funds only |

## What To Prepare For The Bank

Bring this package before asking the bank to open accounts:

| Document | Who Provides It | Notes |
| --- | --- | --- |
| Articles/certificate of incorporation | Corporate attorney or state filing office | Proves the corporation exists |
| EIN confirmation letter | IRS | Usually CP 575 or EIN confirmation page |
| Bylaws | Corporate attorney | Shows governance rules |
| Board resolution authorizing bank accounts | Corporate attorney | Names authorized signers |
| Ownership chart | Company | Must show U.S. and foreign beneficial owners |
| Shareholder agreement | Corporate attorney | Bank may request it for ownership and control |
| Passports/government IDs | Each beneficial owner | Foreign investors should expect extra KYC |
| Proof of address | Each beneficial owner | Utility bill, bank statement, or government document |
| Source-of-funds documents | Each investor | Bank statements, sale agreements, business income proof, audited statements if available |
| W-8BEN or W-8BEN-E | Foreign investors or foreign entities | Needed for tax status and withholding records |
| W-9 | U.S. company and U.S. investors where requested | Used to certify U.S. taxpayer status |
| Business plan | Company | Include property price range, flip strategy, states, expected volume, and no bank debt policy |
| Expected wire plan | Company | Countries, banks, approximate amounts, timing, purpose |

## Banking Instructions For The Partners

- Pick a bank that is comfortable with foreign beneficial owners and real estate investment activity.

- Tell the bank upfront that the company has U.K. and Belgian beneficial owners and may receive wires from Dubai/UAE or U.S. accounts.

- Do not hide the Dubai source-of-funds path. Banks will likely ask for source and path of funds.

- Each partner should prepare a source-of-funds memo explaining where the money came from and why it is available for investment.

- Each foreign partner should provide passport, address proof, tax residence certificate if available, W-8 form, and bank statements showing the funding path.

- The company should open accounts only in the company name, not in an individual's name.

- All capital wires should reference the legal purpose: equity contribution, loan principal, or capital call.

- Keep loan principal wires separate from interest payments.

- Keep a monthly bank reconciliation and property-by-property cash ledger.

- Before sending money back to foreign partners, the CPA must determine whether withholding applies and whether Form 1042-S reporting is required.

## Practical Bank Selection Criteria

| Criterion | Why It Matters |
| --- | --- |
| Handles foreign beneficial owners | Avoids account denial after formation |
| Real estate investor friendly | Understands frequent closings and title wires |
| Strong wire controls | Reduces fraud and partner disputes |
| Multiple approval levels | Useful for a four-partner venture |
| Good online banking exports | CPA needs clean data |
| Can issue account verification letters quickly | Title companies often need this |
| Comfortable with large cash balances | Company will be all-cash |

# Phase 6 - Tax Withholding And Documentation

## Forms To Collect Before Any Payment

| Form | Who Uses It | When |
| --- | --- | --- |
| Form W-9 | U.S. investors and U.S. corporation | Before payments or closings where U.S. status must be certified |
| Form W-8BEN | Foreign individual investors | Before dividends, interest, or other U.S.-source payments |
| Form W-8BEN-E | Foreign company investors, if any | Before dividends, interest, or other U.S.-source payments |
| Treaty residence certificate | Foreign investors, if claiming treaty benefits | Before reduced withholding is applied |
| Loan agreements | Any lending partner | Before funding |
| Board consents | Company | Before issuing shares, accepting debt, opening bank accounts, or paying distributions |

## Annual Federal Forms

| Form | Plain-English Purpose | Who Handles It |
| --- | --- | --- |
| Form 1120 | U.S. corporate tax return | CPA |
| Form 5472 | Reports transactions with 25% foreign owners and related parties | CPA |
| Form 1042 | Annual withholding tax return for payments to foreign persons | CPA |
| Form 1042-S | Information statement to each foreign payee | CPA |
| Form 8990 | Business interest limitation reporting if applicable | CPA |
| Form 8822-B | Reports address or responsible party changes | CPA/company |

## Closing And FIRPTA Controls

At every property sale, the title company should be told that the seller is a domestic U.S. corporation. The closing file should include:

- Seller's non-foreign certification or Form W-9.

- Corporate good standing certificate if requested.

- EIN confirmation.

- Board or officer authority to sell.

- Title LLC ownership confirmation if a title LLC is the named seller.

- CPA/tax counsel review if the title company tries to impose FIRPTA withholding.

Plain-English point: FIRPTA withholding is aimed at foreign sellers of U.S. real estate. If the seller is the U.S. corporation or a disregarded LLC owned by the U.S. corporation, the buyer/title company should generally not treat the seller as foreign.

# Phase 7 - Operating Controls For Flipping Business

## Property Acquisition Checklist

- Deal source and underwriting sheet.

- Purchase contract reviewed by real estate attorney.

- Title search and title insurance quote.

- Entity buyer confirmed: C corporation or title LLC.

- Repair budget.

- Insurance quote before closing.

- Board or investment committee approval.

- Closing wire approval by at least two authorized people.

- Property ledger opened in accounting system.

- Resale plan and target margin documented.

## Accounting Setup

Use bookkeeping that separates:

- Each property's purchase price.

- Closing costs.

- Repairs and improvements.

- Holding costs.

- Insurance.

- Property taxes.

- Utilities.

- Sale proceeds.

- Partner capital.

- Loan principal.

- Interest expense.

- Dividends/distributions.

- Tax reserves.

For flipping, properties are likely business inventory rather than long-term investments. That means the accounting should be built for dealer/inventory treatment unless the CPA says otherwise.

## Cash Control Rules

- No personal accounts for company funds.

- No undocumented partner advances.

- No distributions without CPA review.

- No interest payments to foreign partners without withholding review.

- Two-person approval for outbound wires.

- Keep title company wiring instructions verified by phone using known numbers.

- Monthly partner report showing cash, inventory, pending deals, taxes reserved, and expected exits.

# Phase 8 - Repatriation Plan

Repatriation means getting money back to the U.K. and Belgian investors. This should be planned before the first payment is made.

| Method | Plain-English Meaning | Tax Result | Review Needed |
| --- | --- | --- | --- |
| Loan principal repayment | Company pays back borrowed money | Usually not withholding if true principal | CPA to confirm loan ledger |
| Interest | Company pays the lender for use of money | Deductible if respected; withholding may apply unless treaty/exemption applies | Tax counsel and CPA |
| Dividend | Company pays owners from profits | Not deductible; withholding generally applies unless treaty reduces it | CPA and treaty review |
| Return of capital | Company returns invested capital | Depends on basis and earnings/profits | Tax counsel |
| Redemption | Company buys back shares | Can be dividend or sale treatment; complex for foreign owners | Tax counsel |
| Liquidation | Company winds down and distributes assets/cash | Can trigger FIRPTA/USRPHC and other issues | Tax counsel |

Recommended sequence:

- Repay true loan principal first if loans exist and terms permit.

- Pay interest only after the CPA confirms withholding and reporting.

- Pay dividends only after corporate tax reserves and state taxes are funded.

- Avoid redemptions and liquidations without a written tax review.

- For foreign owners, prepare Forms 1042-S annually for reportable payments.

# Phase 9 - Scenario-Specific Actions

## Scenario A: U.K. And Belgian Capital Originates From Dubai/UAE

Key point: Dubai banking location does not create U.S.-UAE treaty benefits. The tax question is who owns the money and where that owner is tax resident.

Actions:

- Obtain source-of-funds documentation from the Dubai accounts.

- Confirm whether the U.K. partner is a U.K. tax resident and beneficial owner.

- Confirm whether the Belgian partner is a Belgian tax resident and beneficial owner.

- Do not rely on portfolio interest if either foreign lender owns 10% or more voting power.

- Have counsel review whether treaty interest treatment is better than portfolio interest.

- Document all debt terms before funds are wired.

- Prepare the bank for enhanced KYC because UAE-origin wires may receive extra review.

Professional review required:

- Treaty eligibility.

- Anti-conduit risk.

- Debt/equity risk.

- Related-party interest rate.

- U.S. withholding position.

- U.K./Belgian home-country reporting.

## Scenario B: U.K. Capital From Dubai, Belgian Capital From U.S. Bank Account

Key point: a Belgian investor using a U.S. bank account is still foreign for U.S. tax purposes unless he is actually a U.S. tax resident.

Actions:

- Confirm why the Belgian investor has a U.S. bank account and whether it affects U.S. residency analysis.

- Document the source of the Belgian funds even if the money is already in the United States.

- Treat the Belgian investment as equity or debt based on legal documents, not bank location.

- Collect W-8BEN or W-8BEN-E from the Belgian investor or his entity.

- Review Belgian treaty eligibility.

- Plan repatriation to Belgium before payments are made.

- Confirm whether U.S. bank interest, prior U.S. activities, or U.S. days create other tax issues for the Belgian partner.

Professional review required:

- U.S. residency and NRA status confirmation.

- Belgian home-country tax reporting.

- Treaty benefits.

- Estate tax exposure if direct U.S. shares are held.

- Withholding on interest or dividends.

# Phase 10 - Launch Timeline

| Week | Workstream | Tasks |
| --- | --- | --- |
| Week 1 | Fact gathering | Partner residency, ownership goals, target states, expected annual deal volume, source-of-funds documents |
| Week 1 | Advisor selection | Hire U.S. international tax counsel, CPA, corporate attorney, real estate attorney |
| Week 2 | Structure design | Decide direct ownership vs foreign holding companies, voting rights, equity/debt mix, first-state plan |
| Week 2 | Tax modeling | Compare dividend-heavy, debt-heavy, and hybrid structures under both scenarios |
| Week 3 | Formation | Form corporation, draft governance documents, obtain EIN, prepare stock ledger |
| Week 3 | Banking package | Prepare KYC package, board banking resolutions, business plan, ownership chart, W-8/W-9 forms |
| Week 4 | Bank account | Open operating, acquisition, and tax reserve accounts; set wire approvals |
| Week 4 | Title/entity setup | Form first title LLC if needed, register in first operating state, set title closing templates |
| Week 5 | Accounting setup | Chart of accounts, property ledgers, tax reserve process, CPA reporting calendar |
| Week 6 | First acquisition readiness | Purchase contract templates, insurance, title company packet, closing authority package |
| Ongoing | Compliance | Monthly bookkeeping, quarterly tax estimate review, annual filings, withholding review before payments |

# Forms And Documents Downloaded

The following setup forms were downloaded into:

research/real-estate-jv-tax-2026-06-03/setup-forms/

| File | Purpose |
| --- | --- |
| fss4.pdf | IRS Form SS-4, EIN application |
| iss4.pdf | IRS instructions for Form SS-4 |
| fw9.pdf | IRS Form W-9, U.S. taxpayer certification |
| iw9.pdf | IRS instructions for Form W-9 |
| f8832.pdf | IRS Form 8832, entity classification election, with instructions |
| f8822b.pdf | IRS Form 8822-B, address or responsible party changes |
| p542.pdf | IRS Publication 542, corporations |
| p583.pdf | IRS Publication 583, starting a business and keeping records |
| fincen-boi-page.html | Current FinCEN BOI public page snapshot |

The earlier research archive already includes:

| File Type | Purpose |
| --- | --- |
| Forms 1120 and instructions | U.S. corporate tax return |
| Form 5472 and instructions | Foreign-owned U.S. corporation related-party reporting |
| Forms W-8BEN and W-8BEN-E and instructions | Foreign investor tax status and treaty documentation |
| Forms 1042 and 1042-S | Withholding returns and foreign payee reporting |
| Forms 8288, 8288-A, 8288-B and instructions | FIRPTA withholding materials |
| Form 8990 and instructions | Business interest limitation |
| Form 706-NA and instructions | NRA estate tax filing reference |
| U.S.-U.K. treaty materials | U.K. investor treaty review |
| U.S.-Belgium treaty materials | Belgian investor treaty review |
| IRS Publications 515 and 519 | Withholding and NRA tax rules |

# Documents To Draft

| Document | Owner | Review |
| --- | --- | --- |
| Structure decision memo | Tax counsel | All partners |
| Ownership chart | Corporate attorney | Bank, CPA, tax counsel |
| Articles/certificate of incorporation | Corporate attorney | Counsel |
| Bylaws | Corporate attorney | Counsel |
| Shareholder agreement | Corporate attorney | Tax counsel and all partners |
| Subscription agreements | Corporate attorney | Tax counsel |
| Stock ledger | Corporate attorney/company | CPA |
| Board consents | Corporate attorney | CPA where tax relevant |
| Promissory notes | Corporate attorney | Tax counsel and CPA |
| Transfer pricing/debt memo | Tax counsel/CPA | All partners |
| Banking resolution | Corporate attorney | Bank |
| Source-of-funds memos | Each investor | Bank and counsel |
| Property purchase approval template | Company/attorney | Real estate attorney |
| Closing non-foreign certification template | Real estate attorney/CPA | Title company |
| Compliance calendar | CPA | Company management |

# Critical Questions For The Partners

These must be answered before formation is finalized:

- Are the U.K. and Belgian investors actually tax residents of the U.K. and Belgium?

- Will either foreign investor use a company, trust, or holding vehicle?

- What exact voting percentages are intended?

- Can economic ownership differ from voting ownership?

- How much capital will each partner contribute initially?

- Will any partner be paid management fees, acquisition fees, or service fees?

- Will any foreign partner travel to the U.S. to perform services?

- Which states will the company buy in first?

- How many properties are expected in year one?

- Is the planned exit property-by-property sale, company sale, redemption, or long-term rental conversion?

- Will the company ever use outside private lenders?

- What level of annual compliance cost is acceptable?

# Red-Flag Items

| Red Flag | Why It Is Dangerous |
| --- | --- |
| Foreign partners directly own U.S. corporation shares without estate tax review | U.S. corporation stock is U.S.-situs property for NRA estate tax |
| 25% foreign shareholders lend directly and claim portfolio interest | 10% owner exclusion can disqualify portfolio interest |
| Money is wired before documents are signed | Creates unclear equity/debt treatment |
| Dividends or interest paid without withholding review | Can create IRS penalties and partner tax problems |
| Property sold without seller non-foreign certification | Title company may withhold or delay closing |
| Foreign partners perform U.S. services casually | Can create individual U.S. filing and visa issues |
| No Form 5472 process | Penalties can be severe |
| One bank account with no property ledger | Makes profit, basis, and taxes hard to prove |
| Using treaty rates without W-8 and residency support | Treaty benefits can be denied |
| Treating Dubai source as treaty protection | Source of funds is not treaty residence |

# First 10 Action Items

- Appoint one partner as project coordinator.

- Pick the first two target states for operations.

- Collect tax residence facts from the U.K. and Belgian partners.

- Decide whether foreign holding companies are on the table.

- Hire U.S. international tax counsel and CPA.

- Build a year-one financial model with acquisition volume, margins, expenses, tax reserve, and repatriation assumptions.

- Ask counsel to approve the ownership and capitalization design.

- Form the U.S. C corporation only after the ownership design is approved.

- Apply for EIN and prepare the bank KYC package.

- Open bank accounts and fund only under signed equity or loan documents.

# Practical Financial Model Inputs

Use these fields in the model:

| Input | Why Needed |
| --- | --- |
| Number of flips per year | Drives gross receipts and state activity |
| Average purchase price | Drives capital need |
| Average renovation cost | Drives cash need and profit margin |
| Average closing cost | Needed for true margin |
| Average resale price | Revenue projection |
| Holding period | Cash cycle and carrying costs |
| State tax rate | Net profit projection |
| Federal corporate tax | Net profit projection |
| Interest rate on partner debt | Deduction and withholding model |
| Debt/equity ratio | Capital structure risk |
| Dividend rate | Repatriation model |
| Withholding rate | Foreign investor net proceeds |
| Compliance cost | Real net return |
| Tax reserve percentage | Prevents cash crunch |

# Recommendation For Next Advisor Meeting

Take the advisor this packet and ask for written answers to:

- Should the foreign investors own the U.S. blocker directly or through foreign holding companies?

- What is the safest capitalization mix for year one?

- Can any related-party interest be paid at reduced withholding under the U.K. or Belgian treaty?

- Is portfolio interest unavailable under the expected voting structure?

- What state should the main corporation be formed in?

- Which state registrations are needed for the first target markets?

- What is the annual compliance budget?

- What exact documents must be signed before the first capital wire?

- What closing package should be given to title companies to avoid FIRPTA mistakes?

- What facts would change the answer?

# Suggested Governance Rules

- Any property purchase over a set dollar amount requires approval of at least three partners.

- Any wire over a set dollar amount requires two approvals.

- Any payment to a partner requires CPA review first.

- Any loan amendment requires board approval.

- Any new state expansion requires CPA and attorney review.

- Any foreign investor ownership transfer requires tax counsel review.

- Any redemption, liquidation, or stock sale requires written tax advice.

- Monthly financial statements must show property-level profit and cash.

- Tax reserves are funded before distributions.

- Compliance deadlines are owned by the CPA but monitored by management.

# Best Financial Setup, In Plain Terms

The financially best setup is probably not the most aggressive structure. The venture should optimize for after-tax cash that survives review by banks, title companies, the IRS, and foreign tax authorities.

The strongest starting position is:

- Use the U.S. C corporation blocker for operations.

- Solve estate tax exposure before foreign partners hold U.S. shares directly.

- Use debt only where it has real lender economics and proper withholding support.

- Use treaty benefits only where residency, beneficial ownership, W-8 forms, and limitation-on-benefits rules are documented.

- Keep clean banking and accounting from the first wire.

- Treat professional review as part of the setup cost, not optional overhead.

That approach may cost more upfront, but it reduces the chance that later profits are trapped by withholding errors, estate tax exposure, bank delays, title problems, or IRS penalties.